## Sheet1
Product Backlog
User Story Title | Description | Priority (1 low, 10 high) | Estimate | Date Added
Student Login | As a Student, I can login into the system | 10 | 4 | 2021-01-19
Submit Timesheet | As a Student, I can submit a timesheet | 10 | 6 | 2021-01-19
Timesheet Statistics | As a Student, I can view timesheet statistics | 5 | 5 | 2021-01-19
Timesheet Records | As a Student, I can view timesheet records | 6 | 5 | 2021-01-19
Timesheet Deadline | As a Student, I can view timsheet deadline | 10 | 2 | 2021-01-19
Staff Login | As a Staff, I can login into the system | 10 | 2 | 2021-01-19
Verify Timesheet | As a Staff, I can verify a timesheet | 10 | 5 | 2021-01-19
Timesheet Statistics | As a Staff, I can view timesheet statistics | 5 | 2 | 2021-01-19
Timesheet Records | As a Staff, I can view timesheet records | 6 | 2 | 2021-01-19
Timesheet Deadline | As a Staff, I can view timesheet deadline | 10 | 2 | 2021-01-19
Admin Login | As an Admin, I can login into the system | 10 | 1 | 2021-01-19
Timesheet Records | As an Admin, I can view timesheet records | 4 | 1 | 2021-01-19
Set Timesheet Deadline | As an Admin, I can set a timesheet deadline | 10 | 5 | 2021-01-19
Set Timesheet Reminder | As an Admin, I can set a timesheet reminder | 3 | 5 | 2021-01-19
Set Access | As an Admin, I can set data access for students and staff | 10 | 5 | 2021-01-19
Exporting Timesheet | As an Admin, I can export the timesheet to the Univeristy Human Resource Department | 10 | 6 | 2021-01-19
* 1 story point = 3 hours